## Workplan
Activities | POC | Support | March | April | May | June | July | Comments
Preparation
Initial
Ensure buy-in of in-country management
Confirm dates of exercise
Identification of expatriates who will be participating in exercise
Identify market focal point (MFP)
Share key documents with country team, including draft TOR for PCMMA, TORs for different team roles, PCMMA timeline and key questions for preliminary analysis
Administrative
Provide key administrative contacts to HQ team
Launch visa process for expatriates
Provide supporting materials for visa applications as necessary
Arrange accommodation for expatriates and participants coming from outside the region, as necessary
Arrange for food and refreshments during the classroom portion of the training
Arrange for security briefing for expatriate participants
Coordination
Identification of in-country IRC staff to participate in exercise
Invite staff from other agencies to participate in PCMMA via relevant coordination fora
Produce final participant list
Technical
Finalize TOR for PCMMA
Make key decisions regarding region(s) of assessment, sectors of focus and crisis scenario
Develop plan for desk review and preliminary analysis
Desk review and preliminary analysis
Prepare slideshow/training materials on context
Assign roles and tasks re: exercise preparation to critical market team leaders
Training and assessment materials prepared
Logistics
Book facility for training
Share list of logistical resources and physical materials needed for exercise
Track and document offers of logistical and other contributions from other agencies
Identify resources the IRC Pakistan can contribute to the exercise
Confirm vehicular contributions and/or other forms of support from participating agencies
Prepare and deliver materials for exercise
PCMMA Exercise
International participants arrive in country
Classroom-based field preparation
Data collection
In-classroom analysis and preparation of reports
Communication of results (internal and external)
Report finalized
Market monitoring
Develop plan for regular monitoring of critical markets
Routine market monitoring | [7 empty] | See monitoring plan developed during PCMMA

## Detailed agenda for assessment
Schedule for Niger PCMMA, 2015
| June |  |  |  | July
Activité | sat | sun | mon | tues | wed | thurs | fri | sat | sun | mon | tues | wed | thurs | fri | sat | sun | mon | tues | wed | thurs
| 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
International participants arrive
Team leader workshop
Security and logistics briefings
Training for other team members
Questionnaire trials
Fieldwork preparation
Data collection
Debriefing/in-classroom analysis
Data analysis, recommendation formation, development of report
Communication of results
Departure of international participants